## Action Plan 2023-24 (hidden)
Pillars & Strategic Objectives | Initiative ID | Initiative | Key Activities ID | Key Activities | Out put Indicator (KPI) | Unit of Measurement | Start Date | End Date | Executive Owner | Responsible Unit | Activity Weight | Baseline or Status as of June 2023 | Target For 2023/24 | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Remark | Status as of April 2023 (For Refernce & to Estimate June 2023)
Pillar 1: Sustainable and profitable growth
Strategic Objective 3: Enhance Integrated Channel Model to increase efficiency and optimize customer experience
| 1.3.1 | Develop and implement digital transformation strategy |  |  | Defined implemented Digital vision and Digital transformation strategy |  | 2022-07-01 | Monthly until 2025 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department and Online Banking Department | 100
| 1.3.1 |  | 1.3.1.1 | Define NIB’s digital vision and identify relevant interventions and key digital enablers and capabilities for the future. | Approved Digital Vision Document | Percent | 2022-12-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 25 | [15 empty] | 100
| 1.3.1 |  | 1.3.1.1 | Define NIB’s digital vision and identify relevant interventions and key digital enablers and capabilities for the future. | Approved Digital Vision Document | Percent | 2022-12-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 25 | [15 empty] | 85
| 1.3.1 |  | 1.3.1.2 | Adopt an Omni-channel approach to digital channels to offer uniform and seamless functionalities and customer experience across all E-banking channels | Adopted Omni-Channel Platform | Percent | 2022-12-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 20 | [15 empty] | 100
| 1.3.1 |  | 1.3.1.2 | Adopt an Omni-channel approach to digital channels to offer uniform and seamless functionalities and customer experience across all E-banking channels | Adopted Omni-Channel Platform | Percent | 2022-12-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 20 | [15 empty] | 25
| 1.3.1 |  | 1.3.1.3 | Develop customer use cases to test the degree of seamless, consistent customer experience across all E-banking channels | Developed Customer use cases | Percent | 2022-09-01 | 2022-12-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 10 | [15 empty] | 50
| 1.3.1 |  | 1.3.1.3 | Develop customer use cases to test the degree of seamless, consistent customer experience across all E-banking channels | Developed Customer use cases | Percent | 2022-09-01 | 2022-12-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 10 | [15 empty] | 50
| 1.3.1 |  | 1.3.1.4 | Assess adequacy, feasibility and robustness of planned interventions | Assessment report | Percent | 2023-01-01 | 2023-05-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 10 | [15 empty] | 100
| 1.3.1 |  | 1.3.1.4 | Assess adequacy, feasibility and robustness of planned interventions | Assessment report | Percent | 2023-01-01 | 2023-05-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 10 | [15 empty] | 30
| 1.3.1 |  | 1.3.1.5 | Embark on digital strategy roll-out across channels, customer processes and operations | Implemented Digital strategy | Percent | 2022-12-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 15 | [15 empty] | 25
| 1.3.1 |  | 1.3.1.5 | Embark on digital strategy roll-out across channels, customer processes and operations | Implemented Digital strategy | Percent | 2022-12-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 15 | [15 empty] | 40
| 1.3.1 |  | 1.3.1.6 | Monitor commercial performance against original objectives and targets | Performance Report | Percent | 2022-12-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 10 | [15 empty] | 50
| 1.3.1 |  | 1.3.1.6 | Monitor commercial performance against original objectives and targets | Performance Report | Percent | 2022-12-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 10 | [15 empty] | 50
| 1.3.1 |  | 1.3.1.7 | Continue to refine and adapt the digital strategy based on lessons learnt and customer (internal and external) feedback | Refined digital transformation strategy | Percent | 2022-12-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 10 | [15 empty] | 50
| 1.3.1 |  | 1.3.1.7 | Continue to refine and adapt the digital strategy based on lessons learnt and customer (internal and external) feedback | Refined digital transformation strategy | Percent | 2022-12-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 10 | [15 empty] | 50
| 1.3.2 | Introduce new E-Channels products and services |  |  | Newly launched E-channels products & services |  | 2023-01-01 | Annually until 2025 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department and Online Banking Department | 100
| 1.3.2 |  | 1.3.2.1 | Conduct assessment on the new E-Channels products and services such as Interactive tailors machine (ITMs), virtual Banking centers, international payment cards, contactless services, card less ATM withdrawals, and deposit ATMs. | Assessment reports | No. | 2022-10-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 25 | [15 empty] | 6
| 1.3.2 |  | 1.3.2.1 | Conduct assessment on the new E-Channels products and services (in relation with MB & IB) | Assessment reports | No. | 2022-10-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 25 | [15 empty] | 3
| 1.3.2 |  | 1.3.2.2 | Introduce new E-Channels products and services as per the assessment result | Newly launched E-channels products & services | No. | 2022-10-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 40 | [15 empty] | 6
| 1.3.2 |  | 1.3.2.2 | Introduce new E-Channels products and services as per the assessment result | Newly launched E-channels products & services | No. | 2022-10-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 40 | [15 empty] | 1
| 1.3.2 |  | 1.3.2.3 | Develop Mobile Apps for Halal customer | Developed IFB Mobile App | Percent | 2022-12-01 | 2023-04-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 20
| 1.3.2 |  | 1.3.2.4 | Facilitate IFB customers ATM and POS transaction to be free of charge | IFB ATM/POS Charge free proposal | Percent | 2023-01-01 | 2023-05-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 15
| 1.3.3 | Implement and expand agency banking services |  |  | Meet agency banking service yearly target |  | 2022-07-01 | Monthly until 2025 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 100
| 1.3.3 |  | 1.3.3.1 | Determine locations for deployment of agents across regions | Agent Locations Identified | No. | 2022-10-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 10 | [15 empty] | 3000
| 1.3.3 |  | 1.3.3.2 | Identify and recruit agents | Agent Recruitment | No. | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 20 | [15 empty] | 634
| 1.3.3 |  | 1.3.3.3 | Establish agreement with recruited agents and roll out | No of onboarded Agents | No. | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 50 | [15 empty] | 432
| 1.3.3 |  | 1.3.3.4 | Conduct agent training on policy, processes, service delivery, products and services continuously etc. for the agency banking operations | Training Provided for agency banking operations | No. | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 10 | [15 empty] | 432
| 1.3.3 |  | 1.3.3.5 | Ongoing management & review of the agency banking | Assessment (Review) Report | No. | 2023-03-01 | Monthly until 2025 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 10 | [15 empty] | 7
| 1.3.5 | Enhance presence and functionality of E-Channels |  |  | No. of New functionalities across E-Channels products & services |  | 2022-07-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department and Online Banking Department | 95
| 1.3.5 |  | 1.3.5.1 | Carry out assessment of locations of new ATMs, POS, Merchants, Agents across branches/regions | Assessment Report | No. | 2022-09-01 | 2022-12-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 2 | [15 empty] | 1
| 1.3.5 |  | 1.3.5.2 | Increase ATM footprint to cover viable regions based on vision and growth plan | Increased ATM Footprint | No. | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 6 | [15 empty] | 57
| 1.3.5 |  | 1.3.5.3 | Increase POS footprint to cover viable regions based on vision and growth plan | Increased POS Footprint | No. | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 6 | [15 empty] | 10
| 1.3.5 |  | 1.3.5.4 | Increase Merchants channel footprint to cover viable regions based on vision & growth plan | Increased Merchants Footprint | No. | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 6 | [15 empty] | 1967
| 1.3.5 |  | 1.3.5.5 | Increase functionality throughout all E-Channels products and services. (ATM, POS, third party product and service integrations) | Improved functionalities as per the target | Percent | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 6 | [15 empty] | 100
| 1.3.5 |  | 1.3.5.6 | Increase functionality throughout all E-Channels products and services. (Mobile Banking (MB) and Internet Banking(IB), USSD, Wallet, 3rd party product and service integrations) | Improved functionalities as per the target | Percent | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 10 | [15 empty] | 100
| 1.3.5 |  | 1.3.5.7 | Improve awareness and uptake of E-Channels to reduce physical pressure on branch & drive down operating costs | No. of awareness creation sessions | No. | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 10 | [15 empty] | 9
| 1.3.5 |  | 1.3.5.8 | Improve awareness and uptake of E-Channels to reduce physical pressure on branch & drive down operating costs | No. of awareness creation sessions | No. | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 5 | [15 empty] | 9
| 1.3.5 |  | 1.3.5.9 | Design & implement a POS/Agents/Merchants channels usage incentive scheme | Approved & Implemented incentive scheme | Percent | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 5 | [15 empty] | 50
| 1.3.5 |  | 1.3.5.10 | Replace the oldest POS s (Ingenico) with latest POSs to increase their availability & functionalities | No. of Replaced Old POSs | No. | 2023-01-01 | 2023-05-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 8
| 1.3.5 |  | 1.3.5.11 | Upgrade the older ATM machines with an up-to-date operating systems to increase security, to enable real-time camera monitoring and achieve faster transaction throughput | Upgraded older ATM machines | Percent | 2023-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 5
| 1.3.5 |  | 1.3.5.12 | Reduce the downtime of NIB core banking (host) interface with PSS switch to improve ATM and POS availability and functionality throughout the week | Increased channels Uptime | Percent | 2023-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 8 | [15 empty] | 92
| 1.3.5 |  | 1.3.5.13 | Introduce cash back functionality | No. of newly introduced cash back functionalities | No. | 2023-06-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 8
| 1.3.5 |  | 1.3.5.14 | Introduce a reporting tool for Mobile, Internet, Digital wallet and related channels | Introduced reporting tool for online banking channels | Percent | 2022-10-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 5 | [15 empty] | 50
| 1.3.5 |  | 1.3.5.15 | Develop & implement proper structure & manning aligned with the size, complexity & strategic objectives of the Bank for Digital wallet & Agent Banking (NIB E-Birr) product to make it operational across the Banks's Branch, Customers, Merchants, Agents | Aligned structure with volume of work | Percent | 2022-12-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 5 | [15 empty] | 90
| 1.3.6 | Enhance POS, Agent, Merchant deployment and adoption strategy |  |  | No. of new POS, Agent, Merchant customers |  | 2022-07-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 100
| 1.3.6 |  | 1.3.6.1 | Refine POS, Agent, Merchant deployment strategy | Refined Strategy | Percent | 2022-10-01 | 2023-11-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 50 | [15 empty] | 100
| 1.3.6 |  | 1.3.6.1 | Drive aggressive POS, Agent, Merchant penetration by setting target and monitoring POS, Agent, Merchant target for sales unit | POS, Agent, Merchant Target setted to sales unit | Percent | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 25 | [15 empty] | 50
| 1.3.6 |  | 1.3.6.2 | Monitor targets and reward POS, Agent, Merchant employees that achieve set targets by our bank based on their performance | Implemeneted Monitoring & Rewarding system | Percent | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 25 | [15 empty] | 0
| 1.3.7 | Develop E-Commerce strategy |  |  | E-Commerce strategy with Integrated E-Commerce service providers. |  | 2023-01-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 100
| 1.3.7 |  | 1.3.7.1 | Conduct Assessment on E-Commerce business use case in line with NIB digital strategy | Assesement Report | No. | 2023-01-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 40 | [15 empty] | 1
| 1.3.7 |  | 1.3.7.2 | Establish business and technical team to develop, test requirements, implement and expand E-Commerce business | Estabilished Team for E-Commerce business | Percent | 2023-01-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 35 | [15 empty] | 50
| 1.3.7 |  | 1.3.7.3 | Recruit and partner with potential E-Commerce service providers | Estabilished Partnership with E-Commerce service providers | Percent | 2023-01-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 25
Pillar 2: Customer experience excellence
Strategic Objective 5: Enhance customer experience through service excellence and digitalization
| 2.5.1 | Design & Implement seamless customer experience across physical and Digital channels |  |  | Seamless Customer Experience |  | 2022-07-01 | 2023-01-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 100
| 2.5.1 |  | 2.5.1.1 | Identify critical processes that are suitable for all channels |  | Percent | 2022-07-01 | 2023-01-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 25 | [15 empty] | 0
| 2.5.1 |  | 2.5.1.2 | Review and reengineer the identified customer processes to ensure consistent end to end experience in terms of speed and quality of service |  | Percent | 2022-07-01 | 2023-01-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 15
| 2.5.1 |  | 2.5.1.3 | Explore opportunities for integrating the Bank’s systems with external parties |  | Percent | 2022-07-01 | 2023-01-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 20 | [15 empty] | 30
| 2.5.1 |  | 2.5.1.4 | Perform risk assessments to measure the level of security and identify risks that the bank may be exposed to at the time of integration and come up with mitigation measures |  | Percent | 2022-07-01 | 2023-01-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 15
| 2.5.1 |  | 2.5.1.5 | Deploy the reviewed processes across all channels | Deployed Seamless Customer Experience | Percent | 2022-07-01 | 2023-01-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 25
| 2.5.6 | Improve customer satisfaction |  |  | Increased Customer Satisfaction score to 70%, 75% & 80% in the 3 year plan period respectively |  | 2022-07-01 | Monthly until 2025 | ALL Respective V/Ps and Deputy Chiefs | Respective Units | 100
| 2.5.6 |  | 2.5.6.1 | Reduce service delivery time by providing fast, efficient and consistent services | Service delivered as per TAT | Percent | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 10 | [15 empty] | 25
| 2.5.6 |  | 2.5.6.1 | Reduce service delivery time by providing fast, efficient and consistent services | Service delivered as per TAT | Percent | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 10 | [15 empty] | 25
| 2.5.6 |  | 2.5.6.2 | Reduce down time of E-banking channels (MB, IB, Wallet,..) | Up Time rate | Percent | 2022-07-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 10 | [15 empty] | 92
| 2.5.6 |  | 2.5.6.2 | Reduce down time of E-banking channels (ATM, POS,..) | Up Time rate | Percent | 2022-07-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 10 | [15 empty] | 92
| 2.5.6 |  | 2.5.6.8 | Timely address customer complaints | Timely addressed customer complaints | Percent | 2022-07-01 | continuous | Deputy Chief Digital Banking Officer | Online Banking Department | 10 | [15 empty] | 95
| 2.5.6 |  | 2.5.6.8 | Timely address customer complaints | Timely addressed customer complaints | Percent | 2022-07-01 | continuous | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 10 | [15 empty] | 100

## Agency & Card Banking
Pillars & Strategic Objectives | Initiative ID | Initiative | Key Activities ID | Key Activities | Out put Indicator (KPI) | Unit of Measurement | Start Date | End Date | Executive Owner | Responsible Unit | Activity Weight | Baseline or Status as of June 2023 | Target For 2023/24 | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Remark | Status as of April 2023 (For Refernce & to Estimate June 2023)
Pillar 1: Sustainable and profitable growth
Strategic Objective 3: Enhance Integrated Channel Model to increase efficiency and optimize customer experience
| 1.3.1 | Develop and implement digital transformation strategy |  |  | Defined implemented Digital vision and Digital transformation strategy |  | 2022-07-01 | Monthly until 2025 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department and Online Banking Department | 100
| 1.3.1 |  | 1.3.1.1 | Define NIB’s digital vision and identify relevant interventions and key digital enablers and capabilities for the future. | Approved Digital Vision Document | Percent | 2022-12-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 25 | [15 empty] | 100
| 1.3.1 |  | 1.3.1.2 | Adopt an Omni-channel approach to digital channels to offer uniform and seamless functionalities and customer experience across all E-banking channels | Adopted Omni-Channel Platform | Percent | 2022-12-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 20 | [15 empty] | 100
| 1.3.1 |  | 1.3.1.3 | Develop customer use cases to test the degree of seamless, consistent customer experience across all E-banking channels | Developed Customer use cases | Percent | 2022-09-01 | 2022-12-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 10 | [15 empty] | 50
| 1.3.1 |  | 1.3.1.4 | Assess adequacy, feasibility and robustness of planned interventions | Assessment report | Percent | 2023-01-01 | 2023-05-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 10 | [15 empty] | 100
| 1.3.1 |  | 1.3.1.5 | Embark on digital strategy roll-out across channels, customer processes and operations | Implemented Digital strategy | Percent | 2022-12-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 15 | [15 empty] | 25
| 1.3.1 |  | 1.3.1.6 | Monitor commercial performance against original objectives and targets | Performance Report | Percent | 2022-12-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 10 | [15 empty] | 50
| 1.3.1 |  | 1.3.1.7 | Continue to refine and adapt the digital strategy based on lessons learnt and customer (internal and external) feedback | Refined digital transformation strategy | Percent | 2022-12-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 10 | [15 empty] | 50
| 1.3.2 | Introduce new E-Channels products and services |  |  | Newly launched E-channels products & services |  | 2023-01-01 | Annually until 2025 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department and Online Banking Department | 100
| 1.3.2 |  | 1.3.2.1 | Conduct assessment on the new E-Channels products and services such as Interactive tailors machine (ITMs), virtual Banking centers, international payment cards, contactless services, card less ATM withdrawals, and deposit ATMs. | Assessment reports | No. | 2022-10-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 25 | [15 empty] | 6
| 1.3.2 |  | 1.3.2.2 | Introduce new E-Channels products and services as per the assessment result | Newly launched E-channels products & services | No. | 2022-10-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 40 | [15 empty] | 6
| 1.3.2 |  | 1.3.2.4 | Facilitate IFB customers ATM and POS transaction to be free of charge | IFB ATM/POS Charge free proposal | Percent | 2023-01-01 | 2023-05-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 15
| 1.3.3 | Implement and expand agency banking services |  |  | Meet agency banking service yearly target |  | 2022-07-01 | Monthly until 2025 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 100
| 1.3.3 |  | 1.3.3.1 | Determine locations for deployment of agents across regions | Agent Locations Identified | No. | 2022-10-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 10 | [15 empty] | 3000
| 1.3.3 |  | 1.3.3.2 | Identify and recruit agents | Agent Recruitment | No. | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 20 | [15 empty] | 634
| 1.3.3 |  | 1.3.3.3 | Establish agreement with recruited agents and roll out | No of onboarded Agents | No. | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 50 | [15 empty] | 432
| 1.3.3 |  | 1.3.3.4 | Conduct agent training on policy, processes, service delivery, products and services continuously etc. for the agency banking operations | Training Provided for agency banking operations | No. | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 10 | [15 empty] | 432
| 1.3.3 |  | 1.3.3.5 | Ongoing management & review of the agency banking | Assessment (Review) Report | No. | 2023-03-01 | Monthly until 2025 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 10 | [15 empty] | 7
| 1.3.5 | Enhance presence and functionality of E-Channels |  |  | No. of New functionalities across E-Channels products & services |  | 2022-07-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department and Online Banking Department | 95
| 1.3.5 |  | 1.3.5.1 | Carry out assessment of locations of new ATMs, POS, Merchants, Agents across branches/regions | Assessment Report | No. | 2022-09-01 | 2022-12-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 2 | [15 empty] | 1
| 1.3.5 |  | 1.3.5.2 | Increase ATM footprint to cover viable regions based on vision and growth plan | Increased ATM Footprint | No. | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 6 | [15 empty] | 57
| 1.3.5 |  | 1.3.5.3 | Increase POS footprint to cover viable regions based on vision and growth plan | Increased POS Footprint | No. | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 6 | [15 empty] | 10
| 1.3.5 |  | 1.3.5.4 | Increase Merchants channel footprint to cover viable regions based on vision & growth plan | Increased Merchants Footprint | No. | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 6 | [15 empty] | 1967
| 1.3.5 |  | 1.3.5.5 | Increase functionality throughout all E-Channels products and services. (ATM, POS, third party product and service integrations) | Improved functionalities as per the target | Percent | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 6 | [15 empty] | 100
| 1.3.5 |  | 1.3.5.7 | Improve awareness and uptake of E-Channels to reduce physical pressure on branch & drive down operating costs | No. of awareness creation sessions | No. | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 10 | [15 empty] | 9
| 1.3.5 |  | 1.3.5.9 | Design & implement a POS/Agents/Merchants channels usage incentive scheme | Approved & Implemented incentive scheme | Percent | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 5 | [15 empty] | 50
| 1.3.5 |  | 1.3.5.10 | Replace the oldest POS s (Ingenico) with latest POSs to increase their availability & functionalities | No. of Replaced Old POSs | No. | 2023-01-01 | 2023-05-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 8
| 1.3.5 |  | 1.3.5.11 | Upgrade the older ATM machines with an up-to-date operating systems to increase security, to enable real-time camera monitoring and achieve faster transaction throughput | Upgraded older ATM machines | Percent | 2023-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 5
| 1.3.5 |  | 1.3.5.12 | Reduce the downtime of NIB core banking (host) interface with PSS switch to improve ATM and POS availability and functionality throughout the week | Increased channels Uptime | Percent | 2023-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 8 | [15 empty] | 92
| 1.3.5 |  | 1.3.5.13 | Introduce cash back functionality | No. of newly introduced cash back functionalities | No. | 2023-06-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 8
| 1.3.5 |  | 1.3.5.15 | Develop & implement proper structure & manning aligned with the size, complexity & strategic objectives of the Bank for Digital wallet & Agent Banking (NIB E-Birr) product to make it operational across the Banks's Branch, Customers, Merchants, Agents | Aligned structure with volume of work | Percent | 2022-12-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 5 | [15 empty] | 90
| 1.3.6 | Enhance POS, Agent, Merchant deployment and adoption strategy |  |  | No. of new POS, Agent, Merchant customers |  | 2022-07-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 100
| 1.3.6 |  | 1.3.6.1 | Refine POS, Agent, Merchant deployment strategy | Refined Strategy | Percent | 2022-10-01 | 2023-11-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 50 | [15 empty] | 100
| 1.3.6 |  | 1.3.6.1 | Drive aggressive POS, Agent, Merchant penetration by setting target and monitoring POS, Agent, Merchant target for sales unit | POS, Agent, Merchant Target setted to sales unit | Percent | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 25 | [15 empty] | 50
| 1.3.6 |  | 1.3.6.2 | Monitor targets and reward POS, Agent, Merchant employees that achieve set targets by our bank based on their performance | Implemeneted Monitoring & Rewarding system | Percent | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 25 | [15 empty] | 0
Pillar 2: Customer experience excellence
Strategic Objective 5: Enhance customer experience through service excellence and digitalization
| 2.5.6 | Improve customer satisfaction |  |  | Increased Customer Satisfaction score to 70%, 75% & 80% in the 3 year plan period respectively |  | 2022-07-01 | Monthly until 2025 | ALL Respective V/Ps and Deputy Chiefs | Respective Units | 100
| 2.5.6 |  | 2.5.6.1 | Reduce service delivery time by providing fast, efficient and consistent services | Service delivered as per TAT | Percent | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 10 | [15 empty] | 25
| 2.5.6 |  | 2.5.6.2 | Reduce down time of E-banking channels (ATM, POS,..) | Up Time rate | Percent | 2022-07-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 10 | [15 empty] | 92
| 2.5.6 |  | 2.5.6.8 | Timely address customer complaints | Timely addressed customer complaints | Percent | 2022-07-01 | continuous | Deputy Chief Digital Banking Officer | Agency & Card Banking Department | 10 | [15 empty] | 100

## Online Banking
Pillars & Strategic Objectives | Initiative ID | Initiative | Key Activities ID | Key Activities | Out put Indicator (KPI) | Unit of Measurement | Start Date | End Date | Executive Owner | Responsible Unit | Activity Weight | Baseline or Status as of June 2023 | Target For 2023/24 | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Remark | Status as of April 2023 (For Refernce & to Estimate June 2023)
Pillar 1: Sustainable and profitable growth
Strategic Objective 3: Enhance Integrated Channel Model to increase efficiency and optimize customer experience
| 1.3.1 | Develop and implement digital transformation strategy |  |  | Defined implemented Digital vision and Digital transformation strategy |  | 2022-07-01 | Monthly until 2025 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department and Online Banking Department | 100
| 1.3.1 |  | 1.3.1.1 | Define NIB’s digital vision and identify relevant interventions and key digital enablers and capabilities for the future. | Approved Digital Vision Document | Percent | 2022-12-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 25 | [15 empty] | 85
| 1.3.1 |  | 1.3.1.2 | Adopt an Omni-channel approach to digital channels to offer uniform and seamless functionalities and customer experience across all E-banking channels | Adopted Omni-Channel Platform | Percent | 2022-12-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 20 | [15 empty] | 25
| 1.3.1 |  | 1.3.1.3 | Develop customer use cases to test the degree of seamless, consistent customer experience across all E-banking channels | Developed Customer use cases | Percent | 2022-09-01 | 2022-12-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 10 | [15 empty] | 50
| 1.3.1 |  | 1.3.1.4 | Assess adequacy, feasibility and robustness of planned interventions | Assessment report | Percent | 2023-01-01 | 2023-05-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 10 | [15 empty] | 30
| 1.3.1 |  | 1.3.1.5 | Embark on digital strategy roll-out across channels, customer processes and operations | Implemented Digital strategy | Percent | 2022-12-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 15 | [15 empty] | 40
| 1.3.1 |  | 1.3.1.6 | Monitor commercial performance against original objectives and targets | Performance Report | Percent | 2022-12-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 10 | [15 empty] | 50
| 1.3.1 |  | 1.3.1.7 | Continue to refine and adapt the digital strategy based on lessons learnt and customer (internal and external) feedback | Refined digital transformation strategy | Percent | 2022-12-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 10 | [15 empty] | 50
| 1.3.2 | Introduce new E-Channels products and services |  |  | Newly launched E-channels products & services |  | 2023-01-01 | Annually until 2025 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department and Online Banking Department | 100
| 1.3.2 |  | 1.3.2.1 | Conduct assessment on the new E-Channels products and services (in relation with MB & IB) | Assessment reports | No. | 2022-10-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 25 | [15 empty] | 3
| 1.3.2 |  | 1.3.2.2 | Introduce new E-Channels products and services as per the assessment result | Newly launched E-channels products & services | No. | 2022-10-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 40 | [15 empty] | 1
| 1.3.2 |  | 1.3.2.3 | Develop Mobile Apps for Halal customer | Developed IFB Mobile App | Percent | 2022-12-01 | 2023-04-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 20
| 1.3.5 | Enhance presence and functionality of E-Channels |  |  | No. of New functionalities across E-Channels products & services |  | 2022-07-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Agency & Card Banking Department and Online Banking Department | 95
| 1.3.5 |  | 1.3.5.6 | Increase functionality throughout all E-Channels products and services. (Mobile Banking (MB) and Internet Banking(IB), USSD, Wallet, 3rd party product and service integrations) | Improved functionalities as per the target | Percent | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 10 | [15 empty] | 100
| 1.3.5 |  | 1.3.5.8 | Improve awareness and uptake of E-Channels to reduce physical pressure on branch & drive down operating costs | No. of awareness creation sessions | No. | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 5 | [15 empty] | 9
| 1.3.5 |  | 1.3.5.14 | Introduce a reporting tool for Mobile, Internet, Digital wallet and related channels | Introduced reporting tool for online banking channels | Percent | 2022-10-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 5 | [15 empty] | 50
| 1.3.7 | Develop E-Commerce strategy |  |  | E-Commerce strategy with Integrated E-Commerce service providers. |  | 2023-01-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 100
| 1.3.7 |  | 1.3.7.1 | Conduct Assessment on E-Commerce business use case in line with NIB digital strategy | Assesement Report | No. | 2023-01-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 40 | [15 empty] | 1
| 1.3.7 |  | 1.3.7.2 | Establish business and technical team to develop, test requirements, implement and expand E-Commerce business | Estabilished Team for E-Commerce business | Percent | 2023-01-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 35 | [15 empty] | 50
| 1.3.7 |  | 1.3.7.3 | Recruit and partner with potential E-Commerce service providers | Estabilished Partnership with E-Commerce service providers | Percent | 2023-01-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 25
Pillar 2: Customer experience excellence
Strategic Objective 5: Enhance customer experience through service excellence and digitalization
| 2.5.1 | Design & Implement seamless customer experience across physical and Digital channels |  |  | Seamless Customer Experience |  | 2022-07-01 | 2023-01-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 100
| 2.5.1 |  | 2.5.1.1 | Identify critical processes that are suitable for all channels |  | Percent | 2022-07-01 | 2023-01-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 25 | [15 empty] | 0
| 2.5.1 |  | 2.5.1.2 | Review and reengineer the identified customer processes to ensure consistent end to end experience in terms of speed and quality of service |  | Percent | 2022-07-01 | 2023-01-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 15
| 2.5.1 |  | 2.5.1.3 | Explore opportunities for integrating the Bank’s systems with external parties |  | Percent | 2022-07-01 | 2023-01-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 20 | [15 empty] | 30
| 2.5.1 |  | 2.5.1.4 | Perform risk assessments to measure the level of security and identify risks that the bank may be exposed to at the time of integration and come up with mitigation measures |  | Percent | 2022-07-01 | 2023-01-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 15
| 2.5.1 |  | 2.5.1.5 | Deploy the reviewed processes across all channels | Deployed Seamless Customer Experience | Percent | 2022-07-01 | 2023-01-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 25
| 2.5.6 | Improve customer satisfaction |  |  | Increased Customer Satisfaction score to 70%, 75% & 80% in the 3 year plan period respectively |  | 2022-07-01 | Monthly until 2025 | ALL Respective V/Ps and Deputy Chiefs | Respective Units | 100
| 2.5.6 |  | 2.5.6.1 | Reduce service delivery time by providing fast, efficient and consistent services | Service delivered as per TAT | Percent | 2022-09-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 10 | [15 empty] | 25
| 2.5.6 |  | 2.5.6.2 | Reduce down time of E-banking channels (MB, IB, Wallet,..) | Up Time rate | Percent | 2022-07-01 | 2023-06-01 | Deputy Chief Digital Banking Officer | Online Banking Department | 10 | [15 empty] | 92
| 2.5.6 |  | 2.5.6.8 | Timely address customer complaints | Timely addressed customer complaints | Percent | 2022-07-01 | continuous | Deputy Chief Digital Banking Officer | Online Banking Department | 10 | [15 empty] | 95