## POOR PERFORMANCE DC IS
NIB INTERNATIONAL BANK
LIST OF STRATEGIC INITIATIVES & KEY ACTIVITIES THAT HAS POOR PERFORMANCE
AS OF APRIL 30, 2023
Initiative ID | Initiatives | Average Achievement | Key Activities ID. | Key Activities/Deliverables | Out put Indicator (KPI) | Unit of Measurement | Executive Owner | Responsible Unit | Cumulative Target Up to the Month of APRIL | Cumulative Actual Performance Up to the End of the Month of APRIL | Performance Against Target in %
9.5 | Identify, prioritize and automate the bank’s key processes to improve the efficiency and effectiveness of its operation.[In house development]. Eg. Batch file integration; Portal; Share administration; Vacancy management; Website (updating); etc. | 0% | 4.9.5.1 | Identify and document all core and non- core processes to be automated |  | Percent | Deputy Chief Information Systems Officer | Digital Transformation Department | 100 | 0 | 0%
|  |  | 4.9.5.2 | Identify those processes to be automated by internal effort and Others to be addressed by ERP |  | Percent | Deputy Chief Information Systems Officer | Digital Transformation Department | 100 | 0 | 0%
|  |  | 4.9.5.3 | Prioritize the processes to be automated according to their relevance and dependency, and create an implementation plan. |  | Percent | Deputy Chief Information Systems Officer | Digital Transformation Department | 100 | 0 | 0%
|  |  | 4.9.5.4 | Perform requirement gathering & analysis activities |  | Percent | Deputy Chief Information Systems Officer | Digital Transformation Department | 100 | 0 | 0%
|  |  | 4.9.5.5 | Perform System Design |  | Percent | Deputy Chief Information Systems Officer | Digital Transformation Department | 100 | 0 | 0%
|  |  | 4.9.5.6 | Execute the Automation process as per the approval |  | Percent | Deputy Chief Information Systems Officer | Digital Transformation Department | 100 | 0 | 0%
9.7 | Finalize the implementation of remaining CBS Modules: [CRM implementation; FCM implementation; IFB Modules (such as PD module)] | 20% | 4.9.7.1 | Organize project team, define the project life-cycle and milestones and carry out project management activities |  | Percent | Deputy Chief Information Systems Officer | Digital Transformation Department | 100 | 20 | 20%
|  |  | 4.9.7.3 | Carryout the actual implementation, ensure QA is carried out throughout to address the outlined requirements |  | Percent | Deputy Chief Information Systems Officer | Digital Transformation Department | 100 | 0 | 0%
|  |  | 4.9.7.4 | Carryout exhaustive testing and change/risk management during the implementation phase to determine the capabilities of the modules to resolve issues |  | Percent | Deputy Chief Information Systems Officer | Digital Transformation Department | 100 | 0 | 0%
|  |  | 4.9.7.5 | Perform technology and knowledge transfer to ensure that internal team is well equipped to support the system |  | Percent | Deputy Chief Information Systems Officer | Digital Transformation Department | 100 | 0 | 0%
|  |  | 4.9.7.6 | Carry out User Acceptance Testing |  | Percent | Deputy Chief Information Systems Officer | Digital Transformation Department | 100 | 0 | 0%
|  |  | 4.9.7.7 | Migrate data onto the new system and carryout a post implementation review on the migrated data |  | Percent | Deputy Chief Information Systems Officer | Digital Transformation Department | 100 | 0 | 0%
|  |  | 4.9.7.8 | Go live | Finalized CBS module (Mobile & internet Banking) | Percent | Deputy Chief Information Systems Officer | Digital Transformation Department | 100 | 0 | 0%
4.13 | Design and implement a unified, converged and redundant Network and Security Infrastructure. | 46.4% | 4.9.13.7 | Carry out acquisition, Technical testing of the acquired devices as per the BOQ |  | Percent | Deputy Chief Information Systems Officer | IT Infrastructure Management Department IT Risk & Cyber Security Department | 100 | 0 | 0%
|  |  | 4.9.13.8 | Participate in Building, commissioning of the infrastructure |  | Percent | Deputy Chief Information Systems Officer | IT Infrastructure Management Department IT Risk & Cyber Security Department | 30 | 0 | 0%
10.10. | Adopt & Implement technology on risk and compliance data governance | 6.667% | 5.10.1.1 | Develop Business Requirement Document | BRD | Percent | Deputy Chief Information Systems Officer | Core Banking & Business Automation Department | 100 | 20 | 20%
|  |  | 5.10.1.2 | Adopt and implement a GRC solution to aid in the day to day activities of governance, risk, compliance. | Implemented GRC System | Percent | Deputy Chief Information Systems Officer | Core Banking & Business Automation Department | 25 | 0 | 0%
10.15 | Develop a system to automate the risk based internal audit | 2% | 5.10.15.1 | Develop Business Requirement Document | Approved BRD | Percent | Deputy Chief Information Systems Officer | Core Banking & Business Automation Department | 100 | 20 | 20%
|  |  | 5.10.15.2 | Implement a GRC system which includes audit modules that will facilitate and enhance the risk based audits | GRC System | Percent | Deputy Chief Information Systems Officer | Core Banking & Business Automation Department | 25 | 0 | 0%