## Slide 1: TestCommodityExchange Document Management System case study
By: Biruk Abel
April 12, 2017

## Slide 2: Sub topics of the case study
Case 1: Project planning and Project Management
  preparation of a high level project plan that describes critical milestones, main activities to be performed, human resource required, critical success factors to realize the project including its sustainability.
Case 2: Risk Management
  preparation of a risk management plan that gives a high level risk analysis and mitigation plans recommended.

## Slide 3: Contents of project plan(case 1)
Overview
Goal/Statement of work
Objectives
Organization/Roles and responsibilities
High level requirements
Scope
Constraints/assumptions
WBS
Deliverables
Schedule
Success factors

## Slide 4: Overview
This project plan serves as a guide towards implementing a new system called document management system for TestCommodityExchange. It describes all the basic process involved from planning up to project closure phase, i.e. , scope, deliverables, WBS, project schedule, resource planning, critical milestones, risk management, critical success factors to realize the project.

## Slide 5: Goal/Statement of work
To design and implement a document management system for TestCommodityExchange that is accessible by an authenticated user/employees of the exchange both at head office and branch offices.

## Slide 6: Objectives
To prepare and document various phases of the project for example preparation of project plan, risk management plan, quality assurance plan etc.
To establish cost, schedule, list of deliverables, and delivery dates
To establish resources plans
To develop and implement an end to end web based document management system with high availability that allows accessing of documents of the exchange electronically from head office and branch offices.
To deploy and test if the newly developed application not only meets user requirements/expectation but also meets non –functional requirements.
To train end users and deploy the tested and final version of the system.

## Slide 7: Organization/Roles and responsibilities

## Slide 8: High level requirements
Shall allow copying of documents to central server
Shall allow retrieving/viewing/downloading of documents from the central server
Shall register log audits of documents
Shall allow users/employees of TestCommodityExchangeto authenticate with their active directory account.
Shall give role based access to users
Shall maintain a hierarchical folder structure to properly manage documents
Shall allow users to search for documents both by filename and document contents

## Slide 9: High level requirements contd…
Shall check the existence of duplicate documents before uploading a document to the central server.
Shall not allow any characters other than alphabets to be the initial character for the name of a document.
Shall implement an OCR for documents prepared in English language only
Shall able to retrieve/pull a scanned document by using the scanner API with out using any middle ware software/application.

## Slide 10: Scope
The project will not include the development of mobile based app
Will implement OCR (optical character recognition) system to change the scanned document to editable form plus search of a document by its contents.
OCR system for documents prepared with local languages will not be implemented due to time constraints and NLP based applications for local languages is still under research.
The project will only allow authentication of users having active directory credentials created by the exchange, i.e., only employees are allowed to authenticate.
Integration with other systems to access documents generated via other applications.
The automatic retrieving/pulling of a scanned document just by using the scanner’s API won’t be included due to time constraint.

## Slide 11: Scope contd.
The system allow access of documents that belong to three categories
  Documents generated via other internal systems of the exchange for example central depository and clearing and settlement application.
  Scanned documents
  Documents prepared by other text processing software.

## Slide 12: Constraints/Assumptions
There exists a security manager application to integrate with the newly developed application.
There exists web services that allow the exchange of data between existing and the new system to be developed in order to exchange documents generated via other applications.
The time frame set bet senior management is a big constraint. To address the constraint individuals working in the project will work for 14 hours per day including weekends. Plus, some functional requirements have been cut out.
The hard disk space limitation with in the datacenter is another constraint.

## Slide 13: WBS (work break down structure)
No | Activity Name | Dependency | Req. personnel (20) | Milestone
1 | Project planning |  | 3 | PMP,RMP,QAP
1.1 | Project plan and management |  |  | 
1.2 | Risk management plan |  |  | 
1.3 | Quality assurance plan |  |  | 
2 | Requirement specification |  | 2 | RAD

## Slide 14: WBS (work break down structure) contd...
3 | System design | 2 | 2 | System design document
3.1 | system architecture |  |  | 
3.2 | Detail design |  |  | 
4 | Development | 3 | 7 | Actual system
4.1 | Back end development |  |  | 
4.1.1 | Database dev. |  |  | 
4.1.2 | Stored procedure dev. |  |  | 
4.2 | Front end development | 4.1 |  | 

## Slide 15: WBS (work break down structure) contd...
4.2.1 | UI design |  |  | 
4.2.2 | Script dev. |  |  | 
4.2.3 | Code behind development |  |  | 
4.2.4 | Web service dev. |  |  | 
4.3 | Integration |  |  | 
5 | Testing | 4 | 2 | TPD (test plan document)
5.1 | Functional testing |  |  | 
5.2 | Performance testing |  |  | 
5.3 | Acceptance testing |  |  | 

## Slide 16: WBS (work break down structure) contd...
6 | Deployment | 5 | 2 | Deployed system
7 | Training | 6 | 2 | Training certificate
8 | Project closure | 7 |  | 

## Slide 17: Deliverables
Phase | Deliverables | Due date
Planning phase | Project management plan document | April 12, 2017
 | Risk management plan document | April 12, 2017
 | Quality assurance plan document | April 12, 2017
Requirement analysis and elicitation | Requirement analysis document | April 15, 2017
System design | System design document | April 18, 2017
Implementation | Actual software with source code | May 8, 2017

## Slide 18: Deliverables contd…
Testing | Test plan document | May17, 2017
Deployment | Deployed software with binary code | May18, 2017
User Manual preparation | User manual document | May 20, 2017

## Slide 19: Schedule

## Slide 20: Success factors
Set realistic objectives and expectations for every one
  both client and team members must have common understanding on requirements and objectives of the project.
Building the right team
  recruited team members should not only be technically skilled but also committed, well behaved, eager to work
Give the team what they need
  after building the right team provide it with an environment (quiet and comfortable office, comfortable chairs, meeting areas, proper equipment etc. ) that encourages productivity and minimizes distractions

## Slide 21: Contents of Risk management(case 2)
Purpose of RMP
Risk assessment
Use of risk assessment
Risk analysis and recommended mitigation

## Slide 22: Purpose of RMP
To assess, identify and prioritize risks
To prepare mitigation strategies for the identified risks and
To control and monitor the risks based on the mitigation strategies

## Slide 23: Risk assessment
is the process of
Identifying hazards.
Analyze or evaluate the risk associated with that hazard.
Determine appropriate ways to eliminate or control the hazard.

## Slide 24: Use of risk assessment
Create awareness of hazards and risks.
Identify what may be at risk
Determine if existing control measures are adequate or if more should be done.
Prevent crises when done at the design or planning stage.
Prioritize hazards and control measures.

## Slide 25: Risk analysis and recommended mitigation
Risk | Probability | Impact | Description | Mitigation
Personnel availability | low | High | Personnel assigned may not be available during working hours | Create ownership feeling by brainstorming. Assigning a dedicated personnel and inform the risk of not being available.
Personnel skills | low | High | Personnel assigned didn’t have the skills required | Make through assessment about personnel skills before assignment to the task

## Slide 26: Risk analysis and recommended mitigation contd…
schedule | high | high | The time set with the senior management may not be sufficient to produce quality system | Increase the time duration that each team works. Team members are expected to work 24/7 for 14 hours each day.
security | high | high | The security policy set may not be secured enough to deny access to unauthorized users. | Use role base security to access gain access to the system. Plus allow only high level officials to access top secret documents.

## Slide 27: Risk analysis and recommended mitigation contd…
File replication | high | high | Documents might be duplicated on multiple user machine and central server. | To avoid file duplication on the central server before uploading documents onto the server check if there exists an equivalent document that is already uploaded by using document comparison algorithms.
System performance issue | low | medium | System might not respond to user’s action on time. | Through performance testing and use load balancing on application servers.

## Slide 28: Risk analysis and recommended mitigation contd…
Undiscovered bugs during testing | low | high | Untested bugs may occur after deployment. | Test the system in an environment that is very much similar with the one used by users
Availability | high | high | System may become unavailable to users. | Redundancy of the application on multiple application servers.
Continuous change request | high | high | System requirements may change during development or after deployment. | Ensure that a change control process is established that limits changes to those essential to the business

## Slide 29: Risk analysis and recommended mitigation contd…
Unusable backup data | High | High | Backup data may not be usable if restore testing has not been done. | Prepare a restore test plan and perform restore testing on the already backed up data.
No DR site | High | High | If the central data center is down system may not be available. | In cases the main DR is not ready yet. A thoroughly tested mini DR must be ready for such cases.
Hard disk space limitation | high | high | It would be difficult for users to find free space where they can upload documents using the new system. | Four options exist. First option, to upgrade server’s hard disk capacity. Second, the system will use file compression mechanism to decrease file size.

## Slide 30: Risk analysis and recommended mitigation contd…
 |  |  |  | Third, use secured cloud storage services. Forth, the system can be used phase by phase first by senior management then by managers finally all employees.

## Slide 31: Thank You Q & A